MobileApp1

Build Roadmap — Frappe + ERPNext

Admin Dashboard  ·  Mobile Application  ·  ERPNext Integration

Version 1.0  |  May 2026

| 7 Phases | ~36 Weeks | 17 Dashboard Modules | 12 Mobile Modules | 4 Integrations |
| --- | --- | --- | --- | --- |

CONFIDENTIAL — Internal Use Only

# Overview & Principles

This roadmap covers building MobileApp1 from scratch on Frappe Framework with ERPNext as the core ERP backend (ZAP). The build is structured into 7 sequential phases. Each phase produces shippable, testable output before the next begins.

| Stack | Frappe Framework + ERPNext (same bench instance) |
| --- | --- |
| Custom App | mobileapp1 — a custom Frappe app installed alongside ERPNext |
| Mobile Client | React Native or Flutter — separate codebase, calls Frappe REST API |
| Database | MariaDB (managed by Frappe bench) |
| Background Jobs | Frappe Scheduler (Python) for sync, retries, alerts |
| Auth (mobile) | Zitadel SSO — JWT tokens validated by Frappe custom middleware |
| Offline Sync | SQLite on device + outbox worker calling Frappe REST endpoints |
| File Storage | Frappe File Manager or S3-compatible bucket for receipt images |
| External APIs | CMMS and CONNECT — Python adapter classes in custom app |
| ZAP (ERPNext) | Direct DocType operations — no HTTP calls needed for ERP writes |

Core principles:

- Build ERPNext-native first — reuse existing DocTypes (Expense Claim, Timesheet, Payment Entry, Journal Entry) before creating custom ones.

- Every phase ends with a working demo. No phase starts until the previous one is tested.

- Mobile API contracts are defined in Phase 2 and frozen — mobile development can begin in parallel from Phase 3 onward.

- All external integrations (CMMS, CONNECT) are built with adapter classes so the underlying API can change without touching business logic.

- Role permissions are configured from day one — not retrofitted at the end.

# Phase Map

| # | Phase | Timeline | Scope |
| --- | --- | --- | --- |
| 1 | Foundation & Environment | Weeks 1–2 | Bench setup, custom app scaffold, ERPNext config, roles, CI |
| 2 | Master Data Management | Weeks 3–7 | Geography, Users, Positions, Beats, Outlets, Products, Company Profile, Configurations |
| 3 | Operations & Transactions | Weeks 8–14 | Orders, Payments + Denomination, Expenses, Timesheets, Material/Asset Requests, Vendor Onboarding |
| 4 | Attendance & Field Tracking | Weeks 15–18 | Attendance Tracking, GPS Visit Records, Map View, Journey View |
| 5 | Analytics, Reporting & Alerts | Weeks 19–23 | Performance Dashboard, Sales Reports, KPI Reports, Target Tracking, Alerts & Notifications |
| 6 | Mobile Application | Weeks 24–32 | All 12 mobile modules — auth, attendance, visits, orders, payments, expenses, timesheets, props, official work, offline sync |
| 7 | Integration, QA & Launch | Weeks 33–36 | CMMS & CONNECT hardening, E2E testing, UAT, performance tuning, production deployment |

Phase 1 · Weeks 1–2 Foundation & Environment

Goal: A running Frappe bench with ERPNext, the custom app scaffolded, roles defined, and CI/CD in place. No feature code yet — just a solid base everything else will build on.

1.1 Bench & ERPNext Setup

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| Provision server (Ubuntu 22 LTS, 8–16 GB RAM) | Server ready | Use dedicated VM or cloud instance |
| Install Frappe bench (bench init) | Bench running | Python 3.11+, Node 18+ |
| Install ERPNext on the bench | ERPNext accessible | Latest stable v15 |
| Create production site + SSL | HTTPS site live | Nginx + Let's Encrypt |
| Configure MariaDB, Redis, Supervisor | All services stable | bench setup-production |
| Configure scheduled jobs (bench scheduler) | Scheduler enabled | Required for sync jobs later |

1.2 Custom App Scaffold

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| bench new-app mobileapp1 | App folder created | Python package structure |
| bench install-app mobileapp1 on site | App installed | Verify in installed apps list |
| Set up Git repo, branch strategy (main/dev/feature/*) | Repo live | GitHub / GitLab |
| Configure bench CI (GitHub Actions or Frappe CI) | CI pipeline running | Lint + basic test on PR |
| Add pre-commit hooks (flake8, eslint) | Code quality gate |  |

1.3 ERPNext Base Configuration

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| Configure Company in ERPNext (matches client entity) | Company record | Currency, fiscal year |
| Set up Chart of Accounts for settlement Journal Entries | Accounts ready | Debit/Credit accounts for cash & bank |
| Configure Expense Claim Types | Expense types list | Map to field rep expense categories |
| Configure Timesheet Activity Types | Activity types list | Used in M-10 timesheet sync |
| Enable relevant ERPNext modules only | Clean ERPNext UI | Disable unused modules to reduce noise |

1.4 Roles & Permissions Framework

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| Create custom roles: MobileApp Admin, MobileApp Manager, Field Sales Rep | 3 roles created |  |
| Map roles to ERPNext roles where applicable | Role mapping doc | e.g. Manager → Accounts Manager for JE |
| Define permission matrix document (all DocTypes × roles) | Permission matrix | Reference for all future DocTypes |
| Create System Settings defaults (date format, timezone) | Settings locked | IST timezone |

Phase 2 · Weeks 3–7 Master Data Management

Goal: All master data DocTypes built, importable via CSV, and manageable from the admin dashboard. Roles and validations enforced. Mobile API contracts for master data defined and documented.

2.1 D-01 · Geography Management

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| DocType: Geography (Name, Level, Parent, ERP ID, Status) | DocType + migrations | Self-referential parent field |
| Level validation: Zone→Region→Territory hierarchy enforced at save() | Python controller | Raise frappe.ValidationError |
| Tree view using Frappe's built-in tree DocType feature | Tree view in dashboard | Set is_tree=1 on DocType |
| List view with Level/Status filters | List view configured | Standard Frappe list filters |
| REST endpoint: GET /api/geography/tree (for mobile cache) | API endpoint | Whitelisted method |

2.2 D-02 · User & Sales Rep Management

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| Extend Frappe User DocType with custom fields: Employee ID (optional), Position, Zone, Company Profile, IMEI, User Type, Module Access flags | Custom fields on User | Use Custom Field, not core edit |
| Module access child table: Invoicing, Payments, Timesheets, Connect, CMMS Retail, CMMS Vendor flags per user | Child table DocType | Drives mobile menu visibility |
| Warehouse profile child table: Warehouse Name + Type (ZAP read-only / CMMS editable) | Child table DocType | ZAP warehouses fetched from ERPNext |
| Dashboard access workflow: send activation code via email/SMS | Workflow + email template | Use Frappe Email Queue |
| App access toggle (independent of dashboard access) | Custom field + controller | Checked at JWT validation |
| Org-chart view (Reports-To tree) | Custom page with JS tree | Use Frappe Web Page or desk page |
| REST endpoint: GET /api/user/profile (mobile login payload) | API endpoint | Returns module flags, IMEI, zone |

2.3 D-03 · Position Management

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| DocType: Position (Name, Code, Level L1-L4, Reporting To, Attached Employee, Status) | DocType | Self-ref Reporting To |
| POSITION_BEATS bridge DocType (position_code + beat_code, composite unique) | Child/bridge DocType | Frappe child table on Position |
| Vacancy indicator: auto-derive from Attached Employee field | Computed field in list view | Override get_list or use report |
| Attach/Detach beats UI on Position form | Form customization | Search dialog + child table |

2.4 D-04 · Beat / Route Management

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| DocType: Beat (Name, Code, Type GT/MT, Territory link, ERP ID, Status) | DocType | Territory must be Geography with Level=Territory |
| Outlet assignment child table on Beat (one outlet = one beat enforced) | Child table + validation | Check no other beat owns this outlet |
| Beat Schedule DocType: day-of-week × outlet list per beat | Beat Schedule DocType | Used to generate mobile daily plan |
| REST endpoint: GET /api/beat/daily-plan?date=&rep= (mobile) | API endpoint | Returns today's outlet list in order |

2.5 D-05 · Outlet Management

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| DocType: Outlet (all fields per spec, Status) | DocType | Mobile unique on mobile number |
| Outlet approval queue: field-submitted outlets arrive as Draft, manager approves to Active | Workflow (Draft→Approved→Rejected) | Frappe Workflow on Outlet DocType |
| Last visit date: computed from Visit DocType, shown in list view | Custom column in list | SQL Report or override get_list |
| Outlet detail: linked views for visits, orders, payments, asset requests | Dashboard links on form | Frappe Form Dashboard links |
| CSV bulk import support | Data Import Tool config | Standard Frappe Data Import |
| REST endpoint: GET /api/outlet/list?beat= (mobile offline cache) | API endpoint | Returns outlets for rep's beat |

2.6 D-06 · Product Master

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| DocType: Product (ERP ID as PK, Name, Division, Primary/Secondary Category, MRP, GST Profile link, Status) | DocType | ERP ID imported from ERPNext Item |
| Price field: read-only, fetched from ERPNext Item Price on form load | Controller fetch | frappe.get_doc('Item Price',...) |
| GST Profile display: show attached GST template from ERPNext Item | Linked field display | ERPNext Item Tax Template |
| Price visibility toggle (show/hide Price field) | Form script toggle | Frappe Form field toggle |
| Must-Sell flag: checkbox field, used in order compliance | Field + report filter |  |
| CSV bulk import | Data Import config |  |
| REST endpoint: GET /api/product/list (mobile offline cache) | API endpoint | Returns active products with GST info |

2.7 D-07 · Company Profile & D-07B · Configurations

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| DocType: Company Profile (Code PK, CONNECT API creds masked, CMMS API creds masked) — ZAP creds removed (ERPNext is local) | DocType | Credentials stored encrypted |
| Link Company Profile to User (mapped at user level, not geography/position) | Link field on User |  |
| Product alias mapping child table (CONNECT alias, CMMS alias per product) | Child DocType |  |
| Account alias mapping child table | Child DocType |  |
| Test API connection buttons (CONNECT, CMMS) on Company Profile form | Form button + whitelisted method | Returns success/fail response |
| DocType: System Configuration (Admin-only, single instance) | Single DocType | is_single=1 |
| Payment Mode config: Cash only / Online only / Cash + Online options | Config field | Drives mobile payment screen options |
| Denomination logic mandatory flag in System Configuration | Config field | Enforced in settlement controller |

Phase 3 · Weeks 8–14 Operations & Transactions

Goal: All transactional flows — orders, payments, expenses, timesheets, asset requests — built with full approval workflows and ERPNext write-back. This is the most complex phase.

3.1 D-08 · Orders Management

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| DocType: Sales Order (custom, not ERPNext SO) — header + line items child table | DocType + child | Stores ZAP Invoice or CONNECT flow type |
| Order line item: Product link, Qty, MRP (fetched), CGST/SGST/IGST auto-calculated, Net Value | Child DocType with tax logic | Tax from ERPNext Item Tax Template |
| Order status machine: PENDING → SUCCESS / FAILED | Status field + controller |  |
| ZAP sync: on approval, create ERPNext Sales Invoice via frappe.get_doc().insert() | Controller method | Direct ERPNext write — no HTTP |
| CONNECT sync: call CONNECT adapter class on submission | Adapter class | mobileapp1/adapters/connect.py |
| Sync status monitor view: PENDING/FAILED orders with manual retry button | Custom report or list view + button |  |
| No-order reason DocType (reason category + text, linked to Visit) | DocType |  |
| Order compilation report (aggregated by product/beat/territory/rep) | Query Report | CSV/Excel export |
| REST endpoint: POST /api/order/submit (mobile) | API endpoint | Validates, stores, queues sync |

3.2 D-09 · Payments Management

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| DocType: Payment Record (Amount, Mode: Cash/Online/Cash+Online, Reference, Outlet, Rep, Status) | DocType | Status: PENDING_APPROVAL→APPROVED→SUCCESS/FAILED |
| Payment approval queue: manager list view with Approve/Reject actions | Custom list view + workflow | Frappe Workflow |
| On approval: create ERPNext Payment Entry via frappe.get_doc().insert() | Controller + ERPNext write | ZAP = ERPNext — direct write |
| DocType: Denomination Settlement (total amount, denomination breakdown child table, bank refs child table, target account) | DocType + 2 child tables |  |
| Denomination logic: mandatory for cash settlements (System Config flag enforced in controller) | Validation in controller | frappe.throw() if not filled |
| Settlement approval: on approve, create Journal Entry in ERPNext (Debit: collection acct, Credit: cash/bank) | Controller + JE creation | Direct ERPNext write |
| Credits & partial payments DocType (credit note / partial against outlet, running balance) | DocType + balance compute | Aggregated balance shown on Outlet form |
| REST endpoints: POST /api/payment/submit, POST /api/settlement/submit | API endpoints |  |

3.3 D-10 · Expenses & Reimbursements

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| Extend ERPNext Expense Claim DocType with custom fields (receipt image URLs, sync status) | Custom fields on Expense Claim | Reuse ERPNext DocType fully |
| Expense approval queue: wrapper list view filtered to PENDING_APPROVAL claims | List view + filter | Standard Frappe list |
| On approval: submit ERPNext Expense Claim (frappe workflow submit) | Controller | ERPNext handles GL entry |
| Receipt image storage: upload to Frappe File / S3, store URL on record | File attachment handling | frappe.attach_file() |
| REST endpoint: POST /api/expense/submit (mobile), POST /api/expense/upload-receipt | API endpoints |  |

3.4 D-11 · Timesheets

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| Use ERPNext Timesheet DocType with custom fields (sync status, mobile submission flag) | Custom fields | Reuse ERPNext DocType fully |
| Timesheet approval queue: manager list view, Approve/Reject actions | Workflow + list view |  |
| On approval: submit ERPNext Timesheet | Controller | ERPNext handles salary/payroll linkage |
| REST endpoint: POST /api/timesheet/submit (mobile) | API endpoint |  |

3.5 D-12 · Prop / Asset & Material Requests

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| DocType: Material Request (custom — distinct from ERPNext MR) — Type, Item, Qty, Outlet, Notes, Status | DocType | Status: PENDING_APPROVAL→APPROVED→REQUEST_CREATED→DEPLOYED/FAILED |
| DocType: Asset Capitalization Request (no approval needed, goes direct to CMMS queue) | DocType | Status: PENDING→REQUEST_CREATED→DEPLOYED/FAILED |
| Material request approval workflow (manager approve → CMMS sync) | Frappe Workflow |  |
| CMMS adapter: POST to CMMS on approval, handle response, write back status | mobileapp1/adapters/cmms.py | Async via Frappe job queue |
| CMMS webhook receiver: endpoint to receive deployment status updates from CMMS | Whitelisted POST endpoint | Updates record status |
| Prop request timeline view: custom Frappe page showing lifecycle timestamps | Custom desk page | HTML + JS timeline component |
| DocType: Vendor (Name, Contact, Mobile, Email, Category, Status, CMMS Supplier link) | DocType | CMMS Supplier details inherited by Vendor Employees |
| Vendor Employees child table on Vendor (inherits CMMS Supplier details) | Child DocType |  |
| REST endpoints: POST /api/material-request/submit, GET /api/material-request/status | API endpoints |  |

Phase 4 · Weeks 15–18 Attendance & Field Tracking

Goal: Full attendance logging, GPS visit records, map visualization, and daily journey view operational in the admin dashboard.

4.1 D-13 · Attendance Tracking

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| DocType: Attendance Log (Rep, Date, Mark Time, GPS Lat, GPS Lng, Status: Present/Absent/Late) | DocType | One record per rep per day |
| Daily attendance log list view (per rep: marked/not marked, GPS, timestamp) | List view + filters |  |
| Attendance calendar view: monthly per rep (custom Frappe page with calendar JS) | Custom desk page | Use FullCalendar or simple grid |
| Team attendance summary: manager sees all reps in territory, attendance % widget | Custom report or dashboard widget | Query Report with % calculation |
| Attendance report export (CSV with GPS + timestamps) | Query Report with CSV export |  |
| Frappe scheduled job: flag reps with no attendance for the day (feeds D-16 alerts) | Scheduled job | Run at end-of-day cutoff |
| REST endpoint: POST /api/attendance/mark (mobile) | API endpoint | Accepts GPS coords + timestamp |

4.2 D-14 · Location & Visit GPS Tracking

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| DocType: Visit GPS Record (Rep, Outlet, Check-in lat/lng, Check-out lat/lng, Distance from outlet, Timestamp, Out-of-range flag) | DocType | Created on every mobile check-in |
| Out-of-range detection: compare check-in coords vs Outlet registered coords, flag if > threshold | Python distance calc in controller | Haversine formula |
| GPS records list view with out-of-range filter | List view |  |
| Map view: custom Frappe page embedding Leaflet.js, plots outlet pin vs actual check-in pin | Custom desk page (HTML/JS) | Leaflet via CDN, no install needed |
| Daily rep journey view: chronological outlet sequence for a rep on a given day | Custom report or desk page | Ordered by check-in timestamp |
| REST endpoint: POST /api/visit/checkin, POST /api/visit/checkout (mobile) | API endpoints | Creates GPS Record on check-in |

Phase 5 · Weeks 19–23 Analytics, Reporting & Alerts

Goal: All reports, dashboards, and alert systems operational. Managers and admins have full visibility into field performance, sync health, and pending actions.

5.1 D-15 · Performance & Sales Analytics

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| Rep performance Query Report: visits/day, order hit rate, productive vs non-productive, must-sell compliance | Query Report (SQL) | Filter by rep, date range, territory |
| Sales analysis Query Report: revenue/volume by product/category/beat/territory/channel, period comparison | Query Report | CSV/Excel export |
| Order compilation report (daily/weekly/monthly, beat/outlet/product/category breakdown) | Query Report |  |
| Payment collections report (by rep, mode, status, date range) | Query Report |  |
| Productivity KPI report: coverage %, strike rate, avg time per visit, outlier detection | Query Report | Outlier = 2 std dev below mean |
| Asset/prop report (by status, type, outlet, territory) | Query Report |  |
| Target vs Actual DocType: Target (rep/beat/product, period, target qty/value), Actual derived from orders | DocType + Query Report | Confirm requirement first (open question #2) |
| Frappe Dashboard: assemble key widgets (KPI numbers, charts) on a single admin home page | Frappe Dashboard config | Standard Frappe Dashboard feature |
| Universal filter consistency: confirm all reports share same filter parameter names | Filter standardization doc |  |

5.2 D-16 · Alerts & Notifications

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| DocType: Notification Preference (User, Alert Type, Channel: in-app/email/push, Active flag) | DocType | Per-user preferences |
| Approval pending alert: Frappe scheduled job counts pending records, pushes in-app notification | Scheduled job + notification | frappe.publish_realtime() for in-app |
| Sync failure alert: triggered by CMMS/CONNECT adapter on failure after retries, creates Alert Log | Alert log DocType + trigger in adapters |  |
| Rep inactivity alert: scheduled job checks attendance + visit logs, flags inactive reps | Scheduled job |  |
| Prop status change notification: triggered by CMMS webhook receiver | Trigger in webhook handler |  |
| Email notification channel: use Frappe Email Queue to send alert emails | Email templates |  |
| Push notification channel (FCM): integrate Firebase Admin SDK, send on relevant triggers | Firebase integration in custom app | Open question #8 — confirm push requirement |
| In-app notification bell: Frappe's built-in notification system | frappe.publish_realtime + bell count |  |

Phase 6 · Weeks 24–32 Mobile Application

Goal: Full mobile app built and connected to Frappe backend. All 12 modules functional, offline-first sync working end-to-end. This is the longest phase — 9 weeks — because the mobile client is a separate codebase.

6.0 Mobile Project Setup

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| Initialize React Native (or Flutter) project, set up folder structure | Project scaffold | React Native recommended for web API teams |
| Set up SQLite local storage layer (via react-native-sqlite-storage or sqflite) | DB helper module | Schema mirrors key Frappe DocTypes |
| Outbox queue module: table with job_type, payload, status, retry_count, idempotency_key | Outbox module | Central to all offline sync |
| Sync worker: background service, reads outbox, calls Frappe REST API, handles retries | Sync worker service | Run on connectivity restore + periodic |
| Zitadel JWT auth: login screen, token storage (Keychain/Keystore), auto-refresh | Auth module |  |
| IMEI capture + send on first login; Frappe validates and binds | IMEI module | react-native-device-info |
| Master data sync on login: fetch and cache beats, outlets, products, account maps to SQLite | Initial sync module | Periodic refresh in background |
| Offline indicator component + sync status bar | UI component | Shows pending count, last sync time |

6.1 M-01 + M-02 · Auth & Attendance

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| Login screen: username/password → Zitadel → JWT → store securely | Login screen |  |
| First-login IMEI binding flow (send IMEI, receive confirmation) | IMEI bind screen |  |
| Attendance mark screen: single tap, GPS captured, stored in SQLite + outbox | Attendance screen | Required before home screen shown |
| Attendance calendar: own history view, present/absent days | Calendar screen |  |
| Session persistence: app stays logged in, re-prompts only if token unrefreshable | Session manager |  |

6.2 M-03 · Home Screen

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| Home screen: Retailing / Official Work / Attendance tiles | Home screen | Tiles driven by module access flags |
| Today's summary card: visits, orders, payments, pending sync count | Summary component | Read from local SQLite |
| Notification bell: in-app notifications from Frappe realtime or polled API | Notification component |  |
| Offline indicator component | Status bar component |  |

6.3 M-04 + M-05 · Visit Management & Outlet Registration

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| Beat plan screen: today's outlets list from SQLite cache, planned vs visited count | Beat plan screen |  |
| Check-in flow: select outlet → capture GPS → distance check → timestamp → store SQLite + outbox | Check-in screen |  |
| Check-out flow: calculate time spent → store visit record in outbox | Check-out screen |  |
| Telephonic visit toggle: bypass GPS requirement, flag on record | Toggle on check-in screen |  |
| Visit history per outlet screen | History screen |  |
| New outlet registration form: all fields, stores locally as draft, syncs to Frappe approval queue | Registration form screen |  |
| Outlet registration status screen (Submitted/Approved/Rejected) | Status screen |  |

6.4 M-06 · Order Taking

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| Order creation: select flow (ZAP Invoice / CONNECT), auto-fill outlet/beat/visit | Order header screen |  |
| Product search and line item entry: search by name/category, enter qty | Product search + line item screen |  |
| Price display (read-only from cache), tax auto-calculation per line | Line item component |  |
| Must-sell compliance: highlight missing must-sell SKUs, show alert | Compliance indicator |  |
| No-order reason capture: prompt if no items added before check-out | Reason capture screen |  |
| Order stored in SQLite + outbox, sync to Frappe, status tracked | Sync flow |  |
| Order history list screen | History screen |  |

6.5 M-07 · Payment Collection

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| Payment submission screen: mode selector (Cash/Online/Cash+Online per system config), amount, reference | Payment screen |  |
| Denomination settlement screen: total amount, denomination breakdown, bank/online references, target account | Settlement screen | Denomination mandatory for cash (config-driven) |
| Credit/partial payment recording screen: record against outlet, show running balance | Credit screen |  |
| Payment status tracking screen (PENDING_APPROVAL→APPROVED→SUCCESS/FAILED) | Status screen |  |
| Payment history list | History screen |  |

6.6 M-08 + M-09 + M-10 · Props, Expenses, Timesheets

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| Material request form: type, item (from cache), qty, outlet, notes | Request form screen |  |
| Request lifecycle timeline screen: Submitted→Approved→Created→Deployed | Timeline screen |  |
| Expense claim form: type, amount, date, description + receipt camera/gallery upload | Expense form screen | Image upload to Frappe file API |
| Timesheet form: period from/to, hours, activity, notes | Timesheet form screen |  |
| Status tracking screens for expenses and timesheets | Status screens |  |

6.7 M-11 · Official Work

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| Official work log form: activity type, description, duration, date (GPS optional) | Form screen | Activity types confirmed via open question #1 |
| Official work history list screen | History screen |  |
| Sync to Frappe backend (outbox pattern) | Sync flow |  |

6.8 M-12 · Offline Sync Engine (Polish)

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| Full outbox audit: verify all record types (visits, orders, payments, attendance, expenses, timesheets, asset requests, outlet registrations) go through outbox | Outbox coverage test |  |
| Idempotency key implementation: UUID generated per record on creation, sent with every API call | Idempotency middleware |  |
| Retry logic: exponential backoff, max 5 retries, then mark FAILED | Retry logic in sync worker |  |
| Sync status UI screen: pending count, last sync time, failed items list with error detail | Sync status screen |  |
| Master data refresh: periodic background pull of beats/outlets/products when online | Refresh scheduler |  |

Phase 7 · Weeks 33–36 Integration, QA & Launch

Goal: Production-ready system. All integrations hardened, full E2E testing passed, UAT signed off, performance validated, and live deployment complete.

7.1 External Integration Hardening

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| CMMS adapter: full retry logic, structured error logging, webhook signature validation | Production-grade adapter |  |
| CONNECT adapter: full retry logic, error logging, timeout handling | Production-grade adapter |  |
| Sync failure alert pipeline: end-to-end test (adapter fails → alert fires → admin sees it) | E2E test |  |
| CMMS webhook: replay protection (idempotency check on incoming webhooks) | Dedup logic |  |
| API credential rotation procedure documented | Runbook |  |

7.2 End-to-End & Integration Testing

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| Write Frappe unit tests for all custom controllers and whitelisted methods | Test suite (pytest) | frappe.tests |
| Mobile integration tests: key user journeys (login → check-in → order → payment → check-out) | Detox or Appium test suite |  |
| Offline sync E2E: create records offline, restore connectivity, verify all sync to Frappe | E2E test |  |
| ERPNext write-back tests: verify Payment Entry, Journal Entry, Expense Claim, Timesheet created correctly | Integration tests |  |
| Permission matrix test: verify each role can and cannot access correct DocTypes/actions | Permission test suite |  |
| Load test: simulate 50+ concurrent mobile sync workers hitting Frappe REST API | Load test report | Use Locust or k6 |

7.3 UAT & Bug Fixes

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| UAT environment setup (staging site, seeded data) | UAT environment |  |
| UAT with field sales reps (mobile app flows) | UAT sign-off sheet | Focus on check-in, order, payment |
| UAT with managers (approval queues, reports, alerts) | UAT sign-off sheet |  |
| UAT with admin (master data, configurations, user management) | UAT sign-off sheet |  |
| Bug triage and fix sprint | Zero P0/P1 bugs | 2-week buffer built into schedule |

7.4 Performance & Production Readiness

| Task / Story | Deliverable | Notes |
| --- | --- | --- |
| Database index review: add indexes on high-query fields (rep, date, status, outlet, beat) | Optimized DB | EXPLAIN ANALYZE on slow queries |
| Frappe Redis cache config: cache master data API responses | Cache layer | frappe.cache().get_value() |
| Mobile APK/IPA build pipeline (CI generates signed builds) | Build pipeline | GitHub Actions |
| Production deployment: bench switch, migrate, restart | Go-live | Off-peak deployment window |
| Monitoring setup: Sentry for errors, Uptime monitor for site, Frappe Error Log alerts | Monitoring live |  |
| Backup and disaster recovery procedure tested | DR runbook | bench backup + offsite storage |
| Handover documentation: admin guide, developer guide, API reference | Documentation package |  |

# Open Questions (Resolve Before Phase Starts)

| # | Question | Detail | Blocks | Priority |
| --- | --- | --- | --- | --- |
| 1 | Official Work scope | Activity types, GPS required, manager approval needed? | Phase 6 M-11 | High |
| 2 | Targets required? | Yes/no. If yes: per user/beat/product, monthly/weekly? | Phase 5 D-15 | Medium |
| 3 | Attendance logic | Single tap or auto on first check-in? Check-out required? | Phase 4 D-13, M-02 | High |
| 4 | Outlet approval | Field-registered outlets — manager approval or immediate? | Phase 2 D-05, Phase 6 M-05 | High |
| 5 | Credits & partial payments | Credit = negative payment? Against invoice or outlet balance? ZAP sync? | Phase 3 D-09, M-07 | High |
| 6 | Vendor onboarding scope | Full CRUD entity? Multi-step onboarding with documents? | Phase 3 D-12 | Medium |
| 7 | Location tracking mode | Real-time GPS (WebSocket) or historical visit GPS only? | Phase 4 D-14 | High |
| 8 | Push notifications | FCM/APNs required or in-app bell only? | Phase 5 D-16, Phase 6 | Medium |
| 9 | Official Work — approval | Does logging require manager approval? Syncs to ERPNext? | Phase 6 M-11 | Medium |
| 10 | Payment mode — Cash+Online | Confirm three modes. How are denominations + online refs captured simultaneously? | Phase 3 D-09, Phase 6 M-07 | High |

# Tech Stack Reference

| Frappe version | v15 (latest stable) |
| --- | --- |
| ERPNext version | v15 (same bench as Frappe) |
| Python | 3.11+ |
| Node.js | 18+ (for Frappe assets build) |
| Database | MariaDB 10.6+ |
| Cache / Queue | Redis 6+ |
| Web Server | Nginx + Gunicorn (managed by bench) |
| Mobile Framework | React Native (recommended) or Flutter |
| Mobile Local DB | SQLite via react-native-sqlite-storage or sqflite |
| Mobile Auth | Zitadel (OIDC/JWT) |
| Maps (admin) | Leaflet.js (CDN, no install) |
| File / Image Storage | Frappe File Manager (local) or S3-compatible bucket |
| Push Notifications | Firebase Admin SDK (FCM) — if push confirmed |
| CI/CD | GitHub Actions |
| Error Monitoring | Sentry (Frappe + mobile) |
| Load Testing | Locust or k6 |

# Phase Summary

| Ph | Weeks | Duration | Key Deliverables |
| --- | --- | --- | --- |
| 1 | 1–2 | 2 wks | Bench, ERPNext, custom app scaffold, roles, CI/CD |
| 2 | 3–7 | 5 wks | All 7 master data modules + Configurations — fully CRUD, importable, API-ready |
| 3 | 8–14 | 7 wks | Orders, Payments + denomination, Expenses, Timesheets, Material Requests, Vendor Onboarding — all with workflows and ERPNext write-back |
| 4 | 15–18 | 4 wks | Attendance Tracking, GPS Visit Records, Map View, Journey View |
| 5 | 19–23 | 5 wks | All reports, performance dashboards, alert system, push notifications |
| 6 | 24–32 | 9 wks | Complete mobile app — all 12 modules, offline sync engine, E2E sync tested |
| 7 | 33–36 | 4 wks | Integration hardening, E2E QA, UAT, load testing, production launch |

Total: 36 weeks  ·  7 phases  ·  29 modules covered

CONFIDENTIAL — Internal Use Only